## Allocations
Vital Point Personas
Milestones: #1 - Project Start #2 - Initial Definition Complete #3 - Prototype Working #4 - MVP Ready |  |  |  |  | #1 (16 Dec 20) |  | #2 (18 Dec 20) | [5 empty] | #3 (24 Dec 20) | [6 empty] | #4 (31 Dec 20)
| No. | Resource | $/hr | Cost | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91
1.0.0 Project Management
1.1.0 Initiation
1.1.1 Project Concept | 1 | Project Manager | 71 | 71 | 1
1.1.2 Risk Profile | 1 | Project Manager | 71 | 35.5 | 0.5
1.1.3 Stakeholder Register and Comms Plan | 1 | Project Manager | 71 | 142 | 2
1.1.4 Project Charter | 1 | Project Manager | 71 | 142 | 2
1.1.5 Work Breakdown Structure | 1 | Project Manager | 71 | 213 | 3
1.2.0 Plan
1.2.1 Schedule | 1 | Project Manager | 71 | 142 |  | 2
1.2.2 Budget | 1 | Project Manager | 71 | 142 |  | 2
1.2.3 Risk Register | 1 | Project Manager | 71 | 71 |  | 1
1.2.4 Position Descriptions | 1 | Project Manager | 71 | 71 |  | 1
1.2.5 RFP | 1 | Project Manager | 71 | 71 |  | 1
1.3.0 Deliver
1.3.1 Status Reports | 1 | Project Manager | 71 | 497 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
1.3.2 Change Log | 1 | Project Manager | 71 | 497 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
1.3.3 Issues Log | 1 | Project Manager | 71 | 497 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
1.4.0 Close
1.4.1 Reflection | 1 | Project Manager | 71 | 426 | [18 empty] | 6
Sub-Total |  |  |  | 3017.5
2.0.0 Design
2.1.0 Front-End
2.1.1 Requirement Definition | 1 | Project Manager | 71 | 142 |  |  | 2
| 1 | Software Eng I | 40 | 80 |  |  | 2
2.1.2 Requirement Refinement | 1 | Project Manager | 71 | 71 |  |  | 1
| 1 | Software Eng I | 40 | 40 |  |  | 1
2.2.0 Back-End
2.2.1 Requirement Definition | 1 | Project Manager | 71 | 142 |  |  | 2
| 1 | Software Eng I | 40 | 80 |  |  | 2
2.2.2 Requirement Refinement | 1 | Project Manager | 71 | 71 |  |  | 1
| 1 | Software Eng I | 40 | 40 |  |  | 1
2.3.0 Analytics
2.3.1 Requirement Definition | 1 | Project Manager | 71 | 71 |  |  | 1
| 1 | Software Eng I | 40 | 40 |  |  | 1
2.3.2 Requirement Refinement | 1 | Project Manager | 71 | 71 |  |  | 1
| 1 | Software Eng I | 40 | 40 |  |  | 1
Sub-Total |  |  |  | 888
3.0.0 Build
3.1.0 Front-End
3.1.1 | 1 | Sofware Eng I | 40 | 3200 |  |  |  | 2 | 2 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 8 | 8
| 1 | Sofware Eng I | 40 | 3200 |  |  |  | 2 | 2 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 8 | 8
3.1.2 | 1 | Sofware Eng I | 40 | 0
| 1 | Sofware Eng I | 40 | 0
3.2.0 Back-End
3.2.1 | 1 | Sofware Eng I | 40 | 0
| 1 | Sofware Eng I | 40 | 0
3.2.2 | 1 | Sofware Eng I | 40 | 0
| 1 | Sofware Eng I | 40 | 0
3.3.0 Analytics
3.3.1 | 1 | Sofware Eng I | 40 | 0
| 1 | Sofware Eng I | 40 | 0
3.3.2 | 1 | Sofware Eng I | 40 | 0
| 1 | Sofware Eng I | 40 | 0
SubTotal |  |  |  | 6400
4.0.0 Test
4.1.0 Front-End
4.1.1 | 1 | Software Eng I | 40 | 0
| 1 | Software Eng I | 40 | 0
4.1.2 | 1 | Software Eng I | 40 | 0
| 1 | Software Eng I | 40 | 0
4.2.0 Back-End
4.1.1 | 1 | Software Eng I | 40 | 0
| 1 | Software Eng I | 40 | 0
4.1.2 | 1 | Software Eng I | 40 | 0
| 1 | Software Eng I | 40 | 0
SubTotal |  |  |  | 0
5.0.0 Document
5.1.0 Plugin Usage
5.1.1 Install | 1 | Technical Writer | 35 | 0
5.1.2 Usage | 1 | Technical Writer | 35 | 0
5.1.3 Uninstall | 1 | Technical Writer | 35 | 0
5.1.4 Support | 1 | Technical Writer | 35 | 0
SubTotal |  |  |  | 0
Total |  |  |  | 10305.5